## Sheet1
Kendal Action Plan
GOALS | ACTIONS | PRIMARY | PARTNER(S) | Update | TIMELINE | DIFFICULTY | KTC CMTTEE/INDIVIDUAL RESPONSIBLE
Difficulty: 1=easy, 2=OK 3=difficult Brown = PRIORITY / Blue = KTC led projects / Green infill = completed
1. Best Arts & Culture Centre in Rural NW
Make better use of existing assets
1.1 Better signage | Outside Kendal on bypass | Kendal Futures | KTC, BID | Brown Signs in place Dec 2015 | done | 1 | Cllr A Robinson
| Within Kendal. I.e. an inventory and review of signage ped & traffic | KTC | All | HM reports available |  | 1 | HM
| Implementation of audit recommendations | KTC | CCC, SLDC, FSB, BID, Futures & bus users group | All recommendations link to current project work | In Progress |  | HM
| At car parks | SLDC | KTC, Cumbria tourism, BID, Futures |  | done | 1 | Cllr G Archibald
| To car parks | SLDC & KTC | KTC, Masterplan Consultant |  |  |  | Environment & Highways Comm
| For potential arts quad- Abbott Hall, Brewery, Wildman St and Factory | KTC | Kendal Attractions | HM Update Oct 2016 |  | 2 | HM
| For railway station both Oxenholme & Kendal | KTC | KTC, Cumbria Tourism, BID, Futures, Network Rail | HM Update Oct 2016 |  | 2 | HM
| Ladder boards for signposting yard shops | SLDC | Futures, BID |  | In Train | 1 | Environment & Highways Comm
1.2 Paid Project Manager/tourist champion | Job Spec, advertise and recruit | KTC | Futures, BID, SLDC | Completed HM in post |  | 2 | Management Comm
1.3 Integrated advertising of events and attractions | Investigation into what is available eg lists of events, parks, history & attractions and how to take forward | KTC | SLDC, Cumbria Tourism, BID | Completed HM Report available |  | 2 | HM
| Website & apps containing Kendal information | New Website | All | HM Update Oct 2016 |  | 1 | HM
| Sense of Place leaflet distribution | KFB | n/a |  | Done | 1 | Kendal Futures
| Trail and Cultural promotion leaflets, creation and distribution in Visitor Hot Spots | KTC | KF, CT, BID and appointed distribution agency | HM Update Oct 2016 |  |  | HM
1.4 Encouragement of conference facilities | Create and publicise an inventory of conference facilities already in existence | New Website | All |  |  | 1 | Cllr G Archibald
1.5 Oxenholme Station changing its name to Kendal | Or in some way including Kendal in the name | KTC | Kendal Futures, Community Rail Partnership, Network Rail | HM Update Oct 2016 |  | 3 | HM
1.6 Promotion of Riverside and Canal | Protect the possibility of future canal restoration | LCRP | All local authority support |  |  | 3 | Cllr Chris Hogg KTC rep
| Support LCRP's new project @kendal to Lancaster Towpath Trail' | LCRP | All local authority support |  |  | 3 | Cllr Chris Hogg KTC rep
1.7 Sport & Activities facilities | Promote concept of athletics track and other facilities | SLDC, CCC |  |  |  | 3 | tbc
| Promote events and regular fixtures | New Website | All |  |  | 2 | Management Comm
| Promote walks around the Kendal area | New Website | All | LIP Application details | In train | 1 | Cllr T Clare - E&H
2. A Vibrant, Green & Successful Market Town
2.1 Vigorous enhancement and promotion of the market place and its environs | Improvement of the public realm at Market Place | CCC, KTC, SLDC | KFB, Kendal BID | Update Jan 2016 | IN progress | 2 | Cllr S Emmott
| Superior variety and type of stalls | KTC, SLDC | KFB, Kendal BID | Update March 2016 |  | 2 | Cllr S Emmott
| Advertising its times and any special markets | New Website | KFB |  |  | 1 | HM
| Festivals markets | New Website | KFB | Grant support for existing festivals |  | 1 | HM
| Engage the college in new ventures at the market | KTC | Kendal College |  | 2017 | 1 | Cllr S Emmott - Xmas Lights
2.2 Improve Public Realm | Better Furniture | SLDC, KTC (env cmtee) | Civic Society,SLDC officer group,CCC |  |  | 1 | Environment & Highways Comm
| Kendal Castle Improvement Project | KTC | SLDC, Historic England, CCC | HM Update Oct 2016 | 2016 | 2 | HM
| Attractive, well signposted parks/open spaces | KTC | SLDC | HM Update Oct 2016 |  | 2 | Environment & Highways Comm
| Yard enhancement eg as per Police Yd. | KTC | Civic Society, CCC, SLDC | HM Update Oct 2016 |  | 2 | John Robinson
2.3 Improve Transport Infrastructure | Clarity as to the design of the town in the future | SLDC | All |  | 2016 | 2 | Cllr S Emmott
| Special parking deals to enhance usage at times of slow trade | SLDC & BID | BID, Futures, FSB |  | done | 1 | Cllr Giles Archibald
| Advocate Northern development route & possibly a Southern relief road | KTC | CCC, SLDC, FSB, BID, Futures | KTC motion in support Feb 1st 2016 |  | 3 | All - Management
| Consider a new bridge in town | CCC | KTC, SLDC | Reference Masterplan |  | 3 | Cllr T Clare
| Review of Bus Provsion | KTC | BID |  |  | 3 | Cllr T Clare
| Busses after 5pm, for special events etc | BID, Futures | BID,CoC, FSB | Update Jan 2016 |  | 2 | Cllr Giles Archibald
| More pedestrian ways | CCC | All |  |  | 3 | Environment & Highways Comm
| More dedicated cycle routes | SLDC/CCC | BID, CCC |  |  | 2 | Environment & Highways Comm
| Review town perimeter car parks, with possible Park and Ride | SLDC | Futures, BID, CCC,KTC | Part of Masterplan remit |  | 3 | Environment & Highways Comm
| Find a better place for taxis @ Market Place & Town Centre | SLDC,CCC | KTC | Part of Masterplan remit |  | 2 | Cllr S Emmott
2.4 Actively encourage housing, business & central town living | Inventory of empty/underutilised property above shops | SLDC | KTC |  |  | 1 | tbc
2.5 Focus on making the evening like a continental town experience |  | BID, Futures | SLDC, KTC |  |  | 2 | Cllr Giles Archibald
2.6 Attract new and higher paid jobs |  | SLDC | Futures | Ongoing, tracked by SLDC (Paul Mountford) |  | 2 | Cllr Giles Archibald
2.7 High quality landscape/environment in respect of current & future new build |  | SLDC | KTC | Ongoing via planning cmt |  | 2 | John Robinson
3. A Place for Creative, Sustainable and Innovative Businesses
3.1 Support businesses in what they need. | In conjuction with Futures and BID | n/a | KTC | HM Update |  | 2 | HM
| Work to enhance transport links | SLDC | Lakes Line User group, Bus user group. |  |  | 3 | Environment & Highways Comm
| Participate in events and festivals showcasing the town eg Comic Arts etc | SLDC/KTC |  | Ongoing - update re grant support |  | 1 | Audit, Grants & Charities Comm
| Understand and support need for more employment land | SLDC CCC | KTC | IN train | Land now available | 1 | Cllr Giles Archibald
| Provide better parking for coaches and motorhomes | SLDC | Futures, BID | In train |  | 2 | Cllr Giles Archibald
3.2 Support incubator units and Enterprise hubs. |  | SLDC | College | Mintworks & Museum hubs (Carol Davis) |  | 1 | Cllr Giles Archibald
3.3 Clear priorities for future funding of projects bringing economic benefit | K Wrap report | Futures | KTC, CCC, BID, FSB, Cumbria Tourism, College, Brewery etc. | Link to report |  | 2 | Cllr A Robinson
3.4 Focus on encouraging young entrepreneurs |  | SLDC | KTC, CCC, BID, Futures | ongoing via SLDC Economic dev team |  | 2 | tbc
3.5 Enhanced broadband |  | CCC | Connect Cumbria |  |  | 1 | tbc
4. Make Kendal an Age and Disabled Friendly Town
| Initiate audit to identify deficiencies in services | KTC | Age UK, disability groups | TC Update Feb 2016 |  | 1 | Cllr Tom Clare
| Engage with age and disability support groups | KTC | Age UK, disability groups |  |  | 1 | Cllr Tom Clare
| Work with NHS and other groups to co-ordinate activity | KTC | Age UK, disability groups |  |  | 2 | Cllr Tom Clare
| Make dementia and disability training available | KTC | Age UK, disability groups |  |  | 1 | Cllr Tom Clare
| Understand actions taken by other towns in the area | KTC | Age UK, disability groups |  |  | 1 | Cllr Tom Clare
Note on E11: Projects: Included in phase 2 of improved signage project
Note on E12: Projects Kendal Station improvements on hold post Kendal Masterplan recommendations. Oxenholme improvements include organising promotiono f new leaflets, branding and website via new posters - HM currently organising.
Note on E16: Projects: HM continuing to represent KTC on Website Finish and Task group, reporting regulary to Management Comm
Note on E18: Copy and content agreed, currently with designers Cactus Creative to launch before Jan 2017.
Note on E20: Projects: As above, Oxenholme to benefit from new promotional posters.
Note on E27: SE Update: - We await North West Electricity to disconnect the supply from the telephone boxes so they can be removed. Hopefully this will be completed by the end of the financial year. - The design for the LED lighting for the Market Place is now in draft form. - Quotes are on-going for the improvement to the electricity supply in the Market Place. - The de-cluttering of the Market Place , removal of the finger post litter bins parking signs and cycle stands -all on-going. - Artistic impressions / drawings for an enhanced Market Place are completed - Public consultation is yet to take place. Extension of the Christmas Lights near the Wakefield Arms and Sands Avenue. The BID paid for the installation of the brackets etc. so the new lights were up this year.
Note on E28: Projects: on hold - CREATE START DATE FOR DISCUSSIONS - late 2016 early 2017 after public realm improvements
Note on E33: Projects: Funding secured from SLDC and CCC. Tender for heritage/interpretation consultant currently live. Project completion deadline June 2017.
Note on E34: Projects: KTC contrbution to Explore Kendal signage upgrade at Abott Hall Park and other green spaces.
Note on E35: Projects: Woolpack Yard improvement options are under development
Note on E41: GA Update: 'bus' subgroup. Members: Geoff Cook, Phil Walker, Giles Archibald, Brian Harrison (FSB) and Sarah Williams(Kendal BID). Objective: to ensure some form of easily accessible and inexpensive transport after 5p.m. We have met twice: In the current environment it is unlikely that we will be able to persuade current bus operators to operate buses any later in the evening than currently. The group discussed various alternatives including: Arranged shared taxes A regular minibus circulating the estates. Use of Bubbal to monitor available shared transport. These ideas are being explored through discussions with interested parties and we expect to meet again in early February.
Note on E51: Projects: Regular meetings set up between KTC & BID. KTC supporting BID & Futures projects financially and as partners
Note on E61: Projects: The Dementia Directory, set up via the Kendal Dementia Action Alliance received several reports that the directory and website is being held up as a model for others, in Cumbria, the north of England and at Alzeihmer's national HQ.