## Green Space & Public Realm
Priority Outcome | Identified Project | Jury recommendation | KTC's Sponsoring Committee | Lead Partner | Support Partners | Budget allocation |  |  | Budget status (Contribution to a wider project or fully funded by KTC) | Delivery Status (0 to be approved, 1 commited, 2 in development or delivery, 3 delivered) | KTC Role
[6 empty] | 2021/22 | 2022/23 | 2023/24
Provide support for enhanced green spaces | Nobles Rest - Entrance improvements |  | E&H | KCS | SLDC | 5000 (carried over) | x | x | Contribution | 1 | Enabler
Provide excellent allotments | Extend the number of KTC allotments and make sharing plots easier to access. | 1a,1c | Allotments & KIB | tbc | tbc | x | x | x | KTC Budget only | 2 | Doer
| Provide free food growing course to new allotment holders | 1d | Allotments & KIB | Waste into wellbeing? |  | x | x | x | n/a | 0 | Commission
| Continue partnership with Kendal Peoples café to encourage allotment holders to donate excess produce and support them to develop their educational work | 2 | Allotments & KIB | KTC | Various | x | x | x | Contribution | 2 | Commission
Increase Biodiversity | Continue support for Cumbria Dark Skies project and Kendal pilot area. |  | E&H | FLD | Various | x | x | x | n/a | 2 | Enabler
| Support phase two of Kendal Composting Project |  | E&H | SLACC | Various | 5000 | x | x | KTC Budget only | 1 | Champion
Kendal Community Forest | Identify areas for potential planting, create opportunities for sponsorship and adoption of trees to nurture. Create a positive narrative regarding planned new planting. Work toward creating an annual tree counting event. | 22a,b,c,d,e | E&H | SLDC | Various | n/a | x | x | n/a | 0 | Champion
Areas are enhanced for young people | Research the feasibility and partnership buy in to create a pump tack | 19 | E&H | SLDC | Various | 2000 | x | x | KTC Budget only - at feasibility stage | 1 | Doer

## Climate Emergency
Priority Outcome | Identified Project | Jury recommendation | KTC's Sponsoring Committee | Lead Partner | Support Partners | Budget allocation |  |  | Budget status (Contribution to a wider project or fully funded by KTC) | Delivery Status (0 to be approved, 1 commited, 2 in development or delivery, 3 delivered) | KTC Role
[6 empty] | 2021/22 | 2022/23 | 2023/24
Improved connectivity, conditions and access to both walking and cycling | Support the creation of the Kendal to Lancaster Towpath Trail (one aspect of improved cycle infrastructure in Kendal) | 19a | E&H | LCRP | all | 5250 | x | x | Contribution | 1 | Enabler
| Continued membership of LCRP | 19a | E&H | LCRP | n/a | 250 | x | x | Contribution | 1 | Doer
| Support the Flood Relief Improved Connectivity Project | 19a | E&H | EA | all | 15000 | x | x | Contribution | 1 | Champion
| Continue to lobby for town wide 20mph speed limits | 19, 20 | E&H | CCC | all | 10000 | x | x | Contribution | 1 | Champion
| Support LCWIP process via engagment and promotion of improvements (see E&H papers March 21) | 19a,d,e | E&H | CCC | all | 5000 | 5000 | 5000 | Contribution | 1 | Enabler
Air Quality improvements | Ivy Screening Project | 22 | E&H | KTC | all | 3,266 (£10,000 LIPs new application needed) | x | x | Fully Funded via KTC (with LIPs grnat) | 1 | Doer
Support Cumbria's carbon neutrality aims by raising awareness and encouraging positive change | Report Jury recommendation progress via recommendation panel | 12a | E&H | KTC | all | 1176 | 1176 | 1176 | KTC budget only | 1 | Doer
| Promote energy and carbon saving advice and awareness | 8, 10e,g,h, 14a,b, 15 | E&H | KTC | Various | 4500 (tbc via existing £11K biodiversity commitment) | x | x | KTC budget only | 0 | Doer & Champion
| Research the feasibility of a food mile awareness project to be delivered in partnership with Kendal BID. | 5,8,24a,b | E&H | Kendal BID | Various | n/a | x | x | n/a | 0 | Champion
| Train Councillors in Carbon Literacy utilising the Carbon Decision wheel and other relevant tools | 13a,b,e,g | E&H | KTC | Various | n/a | x | x | n/a | 0 | Doer
| Encourage and support businesses to reduce footprint, lobby SLDC to reward energy reductions via reduced business rates. | 24a,b. 10f, | E&H | KTC | Various | n/a | x | x | n/a | 0 | Champion
| Support and encourage the creation of a Kendal Community Renewable Energy Company via feasibility research with landowners. Audit current provision to highlight progress and opportunities in partnership with Lancaster University. | 11a & b, 4. | E&H | KTC | Various | n/a | x | x | n/a | 0 | Enabler
Increase biodiversity | Tree planting / scoping projects | See Green Spaces | [8 empty] | n/a
| Kendal Composting Project | [9 empty] | n/a
| Dark Skies Cumbria | [9 empty] | n/a

## Town Centre Vibrancy
Priority Outcome | Identified Project | Jury recommendation | KTC's Sponsoring Committee | Lead Partner | Support Partners | Budget allocation |  |  | Budget status (Contribution to a wider project or fully funded by KTC) | Delivery Status (0 to be approved, 1 commited, 2 in development or delivery, 3 delivered) | KTC Role
[6 empty] | 2021/22 | 2022/23 | 2023/24
Kendal is positively promoted to visitors and arrivals | Continue to co-ordinate the Kendal Leaflet Series | n/a | E&H | KTC | KF | 2500 - check with Chris | x | x | KTC Budget only (potential for BID contribution) | 2 | Doer
| Continue to support Visit Kendal Website | (Promotion platform for awareness projects) | E&H | KF/KTC/BID | KF | Included in KF allocation | x | x | n/a | 2 | Doer & Commission
Improved Kendal Market | Increase the opportunities for local farmers/producers to sell their products by supporting SLDC's re tendering process and stressing the importance of showcasing local produce | 3 | E&H | SLDC | SLDC | x | x | x | n/a | 2 | Champion
Kendal organisations with similar Town Centre Vibrancy and wider Kendal regeneration goals are supported | Kendal Futures Contribution - Funding has been agreed on the condition of regular updates, inclusion in working groups and the intergration of the Jury recommendations where possible. | Multiple as per KTC funding agreement | Mgmt | KF | KTC | 25250 | x | x | Contribution | 2 | Champion, Enable and Commission
Note on B6: Helen Moriarty: Support for Co-ordinator 7750 Delivering the Action Plan 5000 Kendal Destination Website 6000 Kendal Vision Next Steps 5000 Semi-permanent banners in Kirkland 1500

## Aspirations without budget
Previous Action Plan projects without budget allocation | Status
Town centre wayfinding from Oxenholme and Kendal Station | In development via Kendal Futures Vision
Longpool Traffic Island (replace crazy pave with bonded gravel to prevent weeds, poor KTC 'advert') | Not developed
Urban Tree Planting (Reduce current planter clutter) | In development via Kendal Futures Vision
Birdcage Improvement Project | Not developed
Improve Kendal's Night Time Economy | Town Centre Vibrancy projects can complement this aspiration
Art and public realm along the riverbank corridor | KTC are meeting with EA, potential to link to flood relief scheme
Train Townscape manager as Master Composter, move KTC towards using own compost for town centre planting. | Potential to link to the Kendal Composting project?
Kendal Walking Festival | Assume application will follow if needed
Improve visibility , gateway & environs of Kendal Railway Station | In development via Kendal Futures Vision
Support low income households | Mobile CAB can provide energy saving advice
Support excellent sports & activities provision | Not developed
Support Tour of Britain's return to Kendal | Not developed
Plaques on all KTC assets | Needs development due to logo issue
Improve WW1 Memorial | Not developed