## Approved NEW Action Plan
Kendal Town Council - Action Plan for Kendal
Priority | Priority Outcome | Identified Project | Lead Partner | Estimated costs | KTC's Sponsoring Committee | Support Partners | Development Required (no KTC funding allocated) | In Progress (KTC funding provisionally allocated)
[8 empty] | As at 1st April 2017 | 2017/18 | 2018/19 | 2019/20
[8 empty] | £ | £ | £ | £
Sustainable Connectivity | Improve Signage | Yard Signage | KTC | Low | E&H | KF, SLDC |  |  |  |  | 5000
|  | From Oxenholme and Kendal Station | KTC | Low | E&H | KF, CCC | ✓
|  | Simplyfy directional signage | KTC | Low | E&H | KTC, KF |  | 2055 | 3500
|  | Utilise Kendal Brand where possible including KTC banners | KTC | Low | E&H | n/a | ✓
|  | Improve Kendal Street name signage | KTC | Low | E&H | CCC, SLDA |  |  | 3000
| Postively utilise Kendal's railway connections | Link Kendal to Oxenholme more strongly | KTC | Low | E&H |  | ✓
|  | Improve visibility of Kendal Railway Station | KTC | Low | E&H | all |  |  |  |  | 5000
|  | Lakes Line Feasibility Study | LLCRP | Low | E&H | Various |  |  | 2000
|  | Improve gateway to Kendal Railway Station | SLDC | Med | n/a | all | ✓
| Regnenerate Lancaster Canal | Support creation of Towpath Trail | LCRP | Low | n/a | all |  |  | 10000
|  | Continued membership of LCRP | LCRP | Low | n/a | n/a |  |  | 250 | 250 | 250
| Promote Walking | Support Kendal Walking Trails leafet | KTC | Low | E&H | n/a | ✓
|  | Create wheel friendly trail leaflet | KTC | Low | E&H | n/a | ✓
|  | Kendal Walking Festival | KTC | Low |  | n/a |  |  | 1000
| Promote & create dedicated cycling routes | Support Kendal X Concept (Burton Road Project etc) | CCC | Low | n/a | all | ✓
|  | Provide cycle facitilies where required | CCC | Low | n/a | all | ✓
|  | Create continous Riverside Cycling by removing restrictions and improving signage | SLDC | Low | n/a | all |  |  |  |  | 2000
| Support Air Quality Improvement Actions | Research 20mph in residential areas | KTC | Low | Mgmt |  |  |  |  | 10000
|  | Install radar speed gun | KTC | Low | E&H |  |  |  | 1500
|  | Northern Development Route - support strategic study phase 2 | CCC | Med | n/a | All |  | 10000 | 10000 | 10000
|  | Parking deals | BID | Low | n/a | n/a | ✓
|  | Address Taxi parking issues | SLDC | Low | n/a | n/a | ✓
| Priority Outcome | Identified Project | Lead Partner | Estimated costs | KTC's Sponsoring Committee | Support Partners | Development Required (no KTC funding allocated) | In Progress (KTC funding provisionally allocated)
[8 empty] | As at 1st April 2017 | 2017/18 | 2018/19 | 2019/20
[8 empty] | £ | £ | £ | £
Town Centre Vibrancy | Create an improved Kendal Market | Introduce uniformed stalls | SLDC | Med | n/a | all | ✓
|  | Increase the variety and quality of stall produce nicluding support for specialised market days | SLDC | Med | n/a | all | ✓
|  | Support Market Place Improvements (inclusive of grant income) | SLDC | High | n/a | all |  | 4371 | 32629
| Promote Kendal to potential visitors and arrivals | Continue Kendal Leaflet Series (including Group Travel if required) | KTC | Low | mgmt | KF |  | 12241 | 4000 | 2500 | 2500
|  | Visit Kendal Website (utilising Brand and intergrating all festivals and events) | KF/KTC/BID | Low | mgmt | KF |  | 6000 | 0 | 0 | 3000
|  | Support Kendal TIC | KTC | Low | mgmt | BID, SLDC? |  | 5000 | 5000 | 5000 | 5000
| Become the best rural arts & cultural town in the Noth West | Creatively connect art spaces at Abott Hall, Factory, Brewery & Wildman Street | KTC | Low | mgmt | all |  |  |  |  | 2000
|  | Actively support all Kendal festivals | KTC | Low | Festivals & Grants | Various |  |  | £35,000 per financial year via Christmas Lights & Festivals Committee
| Deliver high quality Public Realm Enhancement Projects to improve first impression & encourage investment | Longpool Traffic Island (replace crazy pave with bonded gravel to prevent weeds, poor KTC 'advert') | KTC | Low | E&H | all | ✓ |  | Environment & Highways Committee
|  | Allan Building Entrance (prevent weed growth at cobbles) | KTC | Low | E&H | CCC, Kendal College | ✓
|  | Station Road Advertisement Board (Create gravel surface to prevent weeds) | KTC | Low | E&H | CCC | ✓
|  | Green Wall at Longpool | KTC | Low | E&H | all |  | 0 | 8000 | 3000 | 1000
|  | Repaint Railings | KTC | Low | E&H | various |  | 1540 | 3040
|  | Urban Tree Planting (Reduce planter clutter) | SLDC? | High | E&H | all | ✓
|  | Birdcage Improvement Project | SLDC? | Med | n/a | all | ✓
|  | Finkle Street Heritage Street Lighting (continuation from Kirkland & Market place) | SLDC | High | n/a | all |  | Completion expected Dec 2017
| Support Kendal organisations with similar Town Centre Vibrancy and wider Kendal regneration goals | Funding support towards Kendal Future role | KF/KTC | Low | Mgmt | SLDC |  | 15000 | 7500 | 8000 | 8500
|  | Funding towards Kendal Futures Projects (in line with action plan) | KF/KTC | Low | Mgmt | all |  |  | 8800 | 10000 | 10000
| Improve Kendal's Flood Resiliance | Kendal Community Emergency Planning support | KECPG | Low | Mgmt | Various |  |  | 5000 | 5000
|  | Support EA recommendations | tbc | tbc | tbc | all | ✓
| Improve Kendal's Night Time Economy | Project to be identified | KF | Low | tbc | all | ✓
| Excellent Christmas Light Display | Additional Christmas Lights at Market Place | KTC | Low | CL | all |  |  | 2000
|  | Install mini Christmas trees (maintin and replace flag and tree holders) | KTC | Low | CL | various | ✓
|  | Support Kendal BID to install addiitonal lights | KF | Low | CL | BID |  |  | 2000
| Priority Outcome | Identified Project | Lead Partner | Estimated costs | KTC's Sponsoring Committee | Support Partners | Development Required (no KTC funding allocated) | In Progress (KTC funding provisionally allocated)
[8 empty] | As at 1st April 2017 | 2017/18 | 2018/19 | 2019/20
[8 empty] | £ | £ | £ | £
Green Space Enhancement | Improve Whattsfield Roundabout | Remove crazy pave and improve planting | KTC | Med | E&H | all | ✓
| Improve Rinkfield Play Area | Support resident association with improvements | RRA | Low | E&H | SLDC |  |  | 5000
| Improve Maudes Meadow | Footpath improvements | SLDC | Med | E&H | SLDC |  |  | 15000
| Improve former Canal area | Support improvements & enhancements eg implementing pollinators project, benches, bins, sculptures etc. | tbc | High | E&H | all | ✓
| Riverside Corridor Improvements | Upgrade Riverside Interpretation | KTC | Med | E&H | SLDC |  |  |  | 2000
|  | Improve fencing and overgrown area between Dockray Hall Road and Dockray Bridge | KTC | Med | E&H | SLDC |  |  |  | 2000
|  | Support initiative to utilise New Road as a green space | SLDC | Med | E&H | all | ✓
|  | Support improvements at Abott Hall Park | SLDC | Med | E&H | Lakeland Arts | ✓
|  | Improve paving between Waterside and Abbott Hall park | CCC | High | E&H | all | ✓
|  | Improve Chantry Step area near Strammongate Bridge | KTC | Low | E&H | Various |  |  |  | 4000
| Improve Kendal Castle | Phase one improvements (inclusive of grant income) | KTC | Low (4000 contributed) | E&H | all |  | 12680 | 9320
|  | Improve Beacon Area | SLDC | Low | n/a | KTC | ✓
|  | Creatively link Kendal Castle to Bowling Fell | KTC | Low | E&H | SLDC |  |  |  | 4000
|  | Support further path improvements | SLDC | Low | E&H | CCC | ✓
|  | Support Active Travel improvements | SLDC | Low | E&H | SLDC | ✓
| Improve Nobles Rest | Support improvement project | SLDC | Low | E&H | SLDC | ✓
| Support Woodland Trails | Heron Hill School Woodland Walk | HHS | Low | E&H | n/a |  | 596 | 1404
| Support footpath improvements | Footpath, Birk Hagg to Parkside Road | KTC | Low | E&H | various |  | 0 | 500
|  | Footpath near Romney Bridge | KTC | Low | E&H | tbc | ✓
| Support Pollinator Project | Continue support | SLACC | Low | KIB | Various |  | 1800 | 8822 | 1300 | 1900
| Support Play Area Improvements | Aboott Hall Play Area | SLDC | Med | E&H | various | ✓
|  | Play Areas recommended by SLDC's play audit | SLDC | Med | E&H | various | ✓
| Priority Outcome | Identified Project | Lead Partner | Estimated costs | KTC's Sponsoring Committee | Support Partners | Development Required (no KTC funding allocated) | In Progress (KTC funding provisionally allocated)
[8 empty] | As at 1st April 2017 | 2017/18 | 2018/19 | 2019/20
[8 empty] | £ | £ | £ | £
Health & Wellbeing | Support low income households | Eden & South LakelandCredit Union | ? | Low | Mgmt | ? |  | 3000 | 3000 | 3000
| Make Kendal Dementia friendly | To be indentified | BID aspiration | Low | Mgmt | tbc | ✓
| Support welbeing programmes | To be identified via SLDC | SLDC | Low | Mgmt | tbc | ✓
| Support excellent sports & actvities provision | Contribute to Kendal Rugby Club, Community Sports Hub | ? | Low | AGC | tbc |  |  | 5000
| Priority Outcome | Identified Project | Lead Partner | Estimated costs | KTC's Sponsoring Committee | Support Partners | Development Required (no KTC funding allocated) | In Progress (KTC funding provisionally allocated)
[8 empty] | As at 1st April 2017 | 2017/18 | 2018/19 | 2019/20
[8 empty] | £ | £ | £ | £
Internal KTC Projects & Crosscutting Grant Programme | Create modern office facilities | Refurb downstairs office | KTC | Med | Mgmt | SLDC | ✓
| Provide support to outside organisations to enhance Kendal's arts, culture, sports, socities and clubs. | Various | KTC | High | Audit Grants and Charities | Various |  |  | £36,000 per financial year via Audits, Grants and Charities committee.
| Provide excellent allotment and planting services | Purchase new van | KTC | Med | Mgmt | n/a |  |  | 15000
| Totals | [6 empty] | 74283 | 172265 | 70050 | 46150
Note on G2: Low = less than £15,000 Med = up to £44,000 High = £45,000 +
Note on N5: Microsoft Office User: yr4 £15,000
Note on K7: Microsoft Office User: Part of previous singage, interpretation & publi realm improvements
Note on L7: yr 2 15,000
Note on N11: Microsoft Office User: yr4 £15,000
Note on N21: Microsoft Office User: yr4 £15,000
Note on G27: Low = less than £15,000 Med = up to £44,000 High = £45,000 +
Note on L33: yr 2: 15,000
Note on N36: Microsoft Office User: yr4 £15,000
Note on L41: yr 2: 15,000
Note on M41: yr 3: 15,000
Note on N41: Microsoft Office User: yr4 £15,000
Note on M46: Microsoft Office User: ate increase due to continous flat rate since 2011. In discussion with all funders.
Note on N46: Microsoft Office User: As before, increase proposed from KF.
Note on L47: Microsoft Office User: £2000 Website maintenance & promotion 12hrs per month Anna Bailey 4th Google Ranking for Kendal 2000 active users in August 6000 page views 80% new visitors £1000 Kirkland Banners x4 to promote new branding £1,300 Benchmarking Report (repat of 2013) £1000 Town Centre Footfall counts Springboard commissioned, heat sensitve cameras, comparisons to other towns, date useful in year two to compare trends and useful to encourage new business into town. £3,500 Evening Economy Research Recommendations KF small working group to progress recommendations. Report distributed/avaiable to all.
Note on G54: Low = less than £15,000 Med = up to £44,000 High = £45,000 +
Note on M61: Microsoft Office User: yr 3 £15,000
Note on M62: Microsoft Office User: yr 3 £15,000
Note on M66: Microsoft Office User: r 3 £15,000
Note on K67: Microsoft Office User: Nclusive of grant income. KTC contribution £4000
Note on M69: yr 3 15,000
Note on G79: Low = less than £15,000 Med = up to £44,000 High = £45,000 +
Note on G86: Low = less than £15,000 Med = up to £44,000 High = £45,000 +

## Original Action Plan
Kendal Action Plan
GOALS | ACTIONS | PRIMARY | PARTNER(S) | Update | TIMELINE | DIFFICULTY | KTC CMTTEE/INDIVIDUAL RESPONSIBLE
Difficulty: 1=easy, 2=OK 3=difficult Brown = PRIORITY / Blue = KTC led projects / Green infill = completed
1. Best Arts & Culture Centre in Rural NW
Make better use of existing assets
1.1 Better signage | Outside Kendal on bypass | Kendal Futures | KTC, BID | Brown Signs in place Dec 2015 | done | 1 | Cllr A Robinson
| Within Kendal. I.e. an inventory and review of signage ped & traffic | KTC | All | HM reports available |  | 1 | HM
| Implementation of audit recommendations | KTC | CCC, SLDC, FSB, BID, Futures & bus users group | All recommendations link to current project work | In Progress |  | HM
| At car parks | SLDC | KTC, Cumbria tourism, BID, Futures |  | done | 1 | Cllr G Archibald
| To car parks | SLDC & KTC | KTC, Masterplan Consultant |  |  |  | Environment & Highways Comm
| For potential arts quad- Abbott Hall, Brewery, Wildman St and Factory | KTC | Kendal Attractions | HM Update Oct 2016 |  | 2 | HM
| For railway station both Oxenholme & Kendal | KTC | KTC, Cumbria Tourism, BID, Futures, Network Rail | HM Update Oct 2016 |  | 2 | HM
| Ladder boards for signposting yard shops | SLDC | Futures, BID |  | In Train | 1 | Environment & Highways Comm
1.2 Paid Project Manager/tourist champion | Job Spec, advertise and recruit | KTC | Futures, BID, SLDC | Completed HM in post |  | 2 | Management Comm
1.3 Integrated advertising of events and attractions | Investigation into what is available eg lists of events, parks, history & attractions and how to take forward | KTC | SLDC, Cumbria Tourism, BID | Completed HM Report available |  | 2 | HM
| Website & apps containing Kendal information | New Website | All | HM Update Oct 2016 |  | 1 | HM
| Sense of Place leaflet distribution | KFB | n/a |  | Done | 1 | Kendal Futures
| Trail and Cultural promotion leaflets, creation and distribution in Visitor Hot Spots | KTC | KF, CT, BID and appointed distribution agency | HM Update Oct 2016 |  |  | HM
1.4 Encouragement of conference facilities | Create and publicise an inventory of conference facilities already in existence | New Website | All |  |  | 1 | Cllr G Archibald
1.5 Oxenholme Station changing its name to Kendal | Or in some way including Kendal in the name | KTC | Kendal Futures, Community Rail Partnership, Network Rail | HM Update Oct 2016 |  | 3 | HM
1.6 Promotion of Riverside and Canal | Protect the possibility of future canal restoration | LCRP | All local authority support |  |  | 3 | Cllr Chris Hogg KTC rep
| Support LCRP's new project @kendal to Lancaster Towpath Trail' | LCRP | All local authority support |  |  | 3 | Cllr Chris Hogg KTC rep
1.7 Sport & Activities facilities | Promote concept of athletics track and other facilities | SLDC, CCC |  |  |  | 3 | tbc
| Promote events and regular fixtures | New Website | All |  |  | 2 | Management Comm
| Promote walks around the Kendal area | New Website | All | LIP Application details | In train | 1 | Cllr T Clare - E&H
2. A Vibrant, Green & Successful Market Town
2.1 Vigorous enhancement and promotion of the market place and its environs | Improvement of the public realm at Market Place | CCC, KTC, SLDC | KFB, Kendal BID | Update Jan 2016 | IN progress | 2 | Cllr S Emmott
| Superior variety and type of stalls | KTC, SLDC | KFB, Kendal BID | Update March 2016 |  | 2 | Cllr S Emmott
| Advertising its times and any special markets | New Website | KFB |  |  | 1 | HM
| Festivals markets | New Website | KFB | Grant support for existing festivals |  | 1 | HM
| Engage the college in new ventures at the market | KTC | Kendal College |  | 2017 | 1 | Cllr S Emmott - Xmas Lights
2.2 Improve Public Realm | Better Furniture | SLDC, KTC (env cmtee) | Civic Society,SLDC officer group,CCC |  |  | 1 | Environment & Highways Comm
| Kendal Castle Improvement Project | KTC | SLDC, Historic England, CCC | HM Update Oct 2016 | 2016 | 2 | HM
| Attractive, well signposted parks/open spaces | KTC | SLDC | HM Update Oct 2016 |  | 2 | Environment & Highways Comm
| Yard enhancement eg as per Police Yd. | KTC | Civic Society, CCC, SLDC | HM Update Oct 2016 |  | 2 | John Robinson
2.3 Improve Transport Infrastructure | Clarity as to the design of the town in the future | SLDC | All |  | 2016 | 2 | Cllr S Emmott
| Special parking deals to enhance usage at times of slow trade | SLDC & BID | BID, Futures, FSB |  | done | 1 | Cllr Giles Archibald
| Advocate Northern development route & possibly a Southern relief road | KTC | CCC, SLDC, FSB, BID, Futures | KTC motion in support Feb 1st 2016 |  | 3 | All - Management
| Consider a new bridge in town | CCC | KTC, SLDC | Reference Masterplan |  | 3 | Cllr T Clare
| Review of Bus Provsion | KTC | BID |  |  | 3 | Cllr T Clare
| Busses after 5pm, for special events etc | BID, Futures | BID,CoC, FSB | Update Jan 2016 |  | 2 | Cllr Giles Archibald
| More pedestrian ways | CCC | All |  |  | 3 | Environment & Highways Comm
| More dedicated cycle routes | SLDC/CCC | BID, CCC |  |  | 2 | Environment & Highways Comm
| Review town perimeter car parks, with possible Park and Ride | SLDC | Futures, BID, CCC,KTC | Part of Masterplan remit |  | 3 | Environment & Highways Comm
| Find a better place for taxis @ Market Place & Town Centre | SLDC,CCC | KTC | Part of Masterplan remit |  | 2 | Cllr S Emmott
2.4 Actively encourage housing, business & central town living | Inventory of empty/underutilised property above shops | SLDC | KTC |  |  | 1 | tbc
2.5 Focus on making the evening like a continental town experience |  | BID, Futures | SLDC, KTC |  |  | 2 | Cllr Giles Archibald
2.6 Attract new and higher paid jobs |  | SLDC | Futures | Ongoing, tracked by SLDC (Paul Mountford) |  | 2 | Cllr Giles Archibald
2.7 High quality landscape/environment in respect of current & future new build |  | SLDC | KTC | Ongoing via planning cmt |  | 2 | John Robinson
3. A Place for Creative, Sustainable and Innovative Businesses
3.1 Support businesses in what they need. | In conjuction with Futures and BID | n/a | KTC | HM Update |  | 2 | HM
| Work to enhance transport links | SLDC | Lakes Line User group, Bus user group. |  |  | 3 | Environment & Highways Comm
| Participate in events and festivals showcasing the town eg Comic Arts etc | SLDC/KTC |  | Ongoing - update re grant support |  | 1 | Audit, Grants & Charities Comm
| Understand and support need for more employment land | SLDC CCC | KTC | IN train | Land now available | 1 | Cllr Giles Archibald
| Provide better parking for coaches and motorhomes | SLDC | Futures, BID | In train |  | 2 | Cllr Giles Archibald
3.2 Support incubator units and Enterprise hubs. |  | SLDC | College | Mintworks & Museum hubs (Carol Davis) |  | 1 | Cllr Giles Archibald
3.3 Clear priorities for future funding of projects bringing economic benefit | K Wrap report | Futures | KTC, CCC, BID, FSB, Cumbria Tourism, College, Brewery etc. | Link to report |  | 2 | Cllr A Robinson
3.4 Focus on encouraging young entrepreneurs |  | SLDC | KTC, CCC, BID, Futures | ongoing via SLDC Economic dev team |  | 2 | tbc
3.5 Enhanced broadband |  | CCC | Connect Cumbria |  |  | 1 | tbc
4. Make Kendal an Age and Disabled Friendly Town
| Initiate audit to identify deficiencies in services | KTC | Age UK, disability groups | TC Update Feb 2016 |  | 1 | Cllr Tom Clare
| Engage with age and disability support groups | KTC | Age UK, disability groups |  |  | 1 | Cllr Tom Clare
| Work with NHS and other groups to co-ordinate activity | KTC | Age UK, disability groups |  |  | 2 | Cllr Tom Clare
| Make dementia and disability training available | KTC | Age UK, disability groups |  |  | 1 | Cllr Tom Clare
| Understand actions taken by other towns in the area | KTC | Age UK, disability groups |  |  | 1 | Cllr Tom Clare
Note on E11: Projects: Included in phase 2 of improved signage project
Note on E12: Projects Kendal Station improvements on hold post Kendal Masterplan recommendations. Oxenholme improvements include organising promotiono f new leaflets, branding and website via new posters - HM currently organising.
Note on E16: Projects: HM continuing to represent KTC on Website Finish and Task group, reporting regulary to Management Comm
Note on E18: Copy and content agreed, currently with designers Cactus Creative to launch before Jan 2017.
Note on E20: Projects: As above, Oxenholme to benefit from new promotional posters.
Note on E27: SE Update: - We await North West Electricity to disconnect the supply from the telephone boxes so they can be removed. Hopefully this will be completed by the end of the financial year. - The design for the LED lighting for the Market Place is now in draft form. - Quotes are on-going for the improvement to the electricity supply in the Market Place. - The de-cluttering of the Market Place , removal of the finger post litter bins parking signs and cycle stands -all on-going. - Artistic impressions / drawings for an enhanced Market Place are completed - Public consultation is yet to take place. Extension of the Christmas Lights near the Wakefield Arms and Sands Avenue. The BID paid for the installation of the brackets etc. so the new lights were up this year.
Note on E28: Projects: on hold - CREATE START DATE FOR DISCUSSIONS - late 2016 early 2017 after public realm improvements
Note on E33: Projects: Funding secured from SLDC and CCC. Tender for heritage/interpretation consultant currently live. Project completion deadline June 2017.
Note on E34: Projects: KTC contrbution to Explore Kendal signage upgrade at Abott Hall Park and other green spaces.
Note on E35: Projects: Woolpack Yard improvement options are under development
Note on E41: GA Update: 'bus' subgroup. Members: Geoff Cook, Phil Walker, Giles Archibald, Brian Harrison (FSB) and Sarah Williams(Kendal BID). Objective: to ensure some form of easily accessible and inexpensive transport after 5p.m. We have met twice: In the current environment it is unlikely that we will be able to persuade current bus operators to operate buses any later in the evening than currently. The group discussed various alternatives including: Arranged shared taxes A regular minibus circulating the estates. Use of Bubbal to monitor available shared transport. These ideas are being explored through discussions with interested parties and we expect to meet again in early February.
Note on E51: Projects: Regular meetings set up between KTC & BID. KTC supporting BID & Futures projects financially and as partners
Note on E61: Projects: The Dementia Directory, set up via the Kendal Dementia Action Alliance received several reports that the directory and website is being held up as a model for others, in Cumbria, the north of England and at Alzeihmer's national HQ.